Sachhi Saheli – Integrated NGO ERP

Phased Delivery Plan

This plan sequences the ERP into six delivery phases, based directly on the client's own requirement document ("Sachhi Saheli (NGO) ERP Requirement, v1"). Each phase is a self-contained, working piece of the system, built in an order where every phase only depends on what came before it.

# 1. Key Scope Decision — Responsive Web Instead of a Native App

The system will be delivered as a responsive web application, usable from any device's browser — desktop, tablet or mobile — rather than a separate native Android app with offline storage and sync.

- Field staff use the mobile browser directly; no app to install or update.

- Note for planning: this approach needs an active connection to submit data. Fully offline capture (no signal) is a distinct capability that can be scoped as a later addition if it becomes a firm requirement.

# 2. Payroll — What's Included

The client's requirement document asks for payroll and salary structure, with employee-wise payslips. This is included as follows:

- Included: salary structure per employee, monthly payroll processing, payslip generation, payroll/salary reporting.

- Handled as a separate item: automatic statutory compliance — PF, ESI, gratuity and TDS calculation and filing. This is specialised, regularly-updated compliance logic, and is scoped once the client confirms whether it is needed from day one or can follow later.

# 3. Employee vs Volunteer — Shared Data Model

The client's document describes an "Employee/Volunteer master" — one shared record type with a Person Type field, rather than two separate structures. Profile, attendance and leave work the same way for both; payroll applies to Employees, and whether Volunteer expenses/leave are tracked the same way is confirmed with the client during Phase 2–3 setup.

# 4. Phased Delivery Plan

See the attached "Phased Delivery Flow" diagram for the visual version of this table.

| Phase | What's In | Why This Grouping |
| --- | --- | --- |
| Phase 1 — Foundation & Admin Setup | Organisation setup, RBAC & roles (Admin, HR, Finance, Programme, Field, Management), user accounts with Person Type | Nothing else can be built or logged into before this exists. |
| Phase 2 — HR Core | Employee/Volunteer master, profile & documents, department/designation/reporting hierarchy, joining & exit, attendance (incl. remote), leave & holiday calendar | Gets people into the system and tracked day to day. |
| Phase 3 — HR Payroll & Claims | Payroll & salary structure, payslip, promotion updates, reimbursement & travel/expense claims, emergency advance, HR reports | A distinct, self-contained milestone once core HR is running. |
| Phase 4 — Finance & Accounts | Fund in-flow (donor/project tracking, receipts), fund out-flow (expense entry, vendor & beneficiary payments, approval), financial reports & dashboard | Runs the organisation's money. Needs Phase 1 roles/approvals in place first. |
| Phase 5 — Project & Portfolio Management | Project creation & approval, budget (expected) vs fund allocation (actual), project expenses, closure & completion reporting, beneficiaries, evidence | Ties funding (Phase 4) to actual project delivery. |
| Phase 6 — CRM & Common ERP Layer | Donor/CSR master, beneficiary profile, CRM reports, unified dashboard, in-app notifications, document management, audit trail, MIS/export, mobile responsive | Rounds out the system once the operational core (Phases 1–5) is live. |

# 5. Items Simplified or Deferred

A few items from the wider requirement list are simplified, deferred, or replaced with a more practical approach, without losing the underlying capability:

| Item | Approach |
| --- | --- |
| Native Android app + offline sync | Delivered as a responsive web app instead — see Section 1. |
| Training records (HR) | Not part of the client's requirement list; can be added later if needed. |
| Statutory payroll compliance (PF, ESI, gratuity, TDS) | Scoped separately once confirmed as required — see Section 2. |
| Geo-Tagging & Field Verification as its own module | Folded into Field Activity as a smaller add-on once field capture is live, rather than built as a standalone module. |
| SMS / WhatsApp / Email notification integrations | In-app notifications cover this in Phase 6; third-party channels can be added on request. |
| Future integrations (accounting, biometric, mapping, donor portals, digital signature) | Listed as future items in the client's own document; not part of this build. |
| Four separate dashboards (Management / Project / HR / Finance) | Delivered as one unified, role-based dashboard in Phase 6 — same information, one screen. |
| Configurable approval engine | Delivered as fixed approval chains for leave, travel, purchase and budget, covering the day-to-day need. |
| Standalone Audit & Compliance module | Activity/approval history is kept as part of the Workflow layer instead of a separate audit system. |

# 6. Nothing Moves Ahead of Phase 1

Phase 1 stays exactly as scoped: organisation setup, RBAC and user accounts only. Every other phase depends on it, so it stays first and stays small.

# 7. What Could Move Up From Phase 6

A few Phase 6 items are worth watching, because NGOs are usually judged by donors on exactly this data. Flagging them here so the client can decide — they are not pulled forward by default:

- Evidence & Documentation — photos/records proving activities happened. Donors often ask for this before releasing the next grant tranche.

- M&E (basic indicators only) — target-vs-achievement numbers. Also common in donor reports.

- Donor/CSR CRM (basic) — donor and CSR partner records; the client's document lists this as its own module, separate from Finance.

Recommendation: leave all three in Phase 6 for now, and revisit if a donor reporting deadline requires earlier access to this data.